## How to use
How to use this sheet
1. On the People tab, add one row per person. Enter their working hours, lunch, and working days per week.
2. Set a Daily reserve % for the churn of a normal day, the email, admin, and interruptions that are never billable.
Fifteen to twenty percent is a common honest starting point.
3. Set a Buffer % as daily slack so one late task does not knock over the rest of the week. Ten percent is a sensible default.
4. Enter Meetings/day in hours. Standing meetings are real time, so they come off the top of what a person can put on projects.
5. On the Demand tab, list each live job, choose who it is assigned to, enter the man-hour estimate, and set how many
weeks you want to deliver it in. Read the Fit column.
A green Fits means the person has room. A red Over by means their committed work is above their real capacity, and a job
needs to move, shrink, or shift to someone else. The firm total can look comfortable while one person is over, so always
trust the person level number.
The maths, in full
Gross = working hours - lunch
CWC = Gross x (1 - daily reserve %) the genuinely committable part of a day
Planning target = CWC x (1 - buffer %) where you plan to load a person
Hard ceiling = CWC the maximum before you are certainly overbooking
Plannable/day = Planning target - meetings
Weekly capacity = Plannable/day x working days
Buffer is supply side slack, daily room so one slip does not cascade. It is never padding added to an estimate.
Where a spreadsheet stops
This sheet gives an honest weekly average per person, and that alone beats loading everyone to a nominal 40 hours.
It is also where the manual method runs out of road:
It reports a flat weekly number, so it cannot tell you whether Tuesday is the problem or Friday.
When someone books leave or a client slips a file, nothing moves. A person rebuilds the sheet by hand.
It can tell you someone is over by 4.2 hours a week. It cannot say which deadline moves, or what that knocks on to.
Estimates never learn. Last quarter real durations do not flow into next quarter numbers.
Stasis does those four things automatically. Free for 7 days, no card needed: https://stasis.clavis-data.com
A Clavis product. Questions: support@clavis-data.com

## People & Capacity
Person | Role | Working hours/day | Lunch (h) | Daily reserve % | Buffer % | Meetings/day (h) | Working days/week | Gross/day (h) | CWC/day (h) | Planning target/day (h) | Hard ceiling/day (h) | Plannable/day (h) | Weekly capacity (h) | Committed/wk (h) | Free/wk (h) | Status
Amir | Lead Consultant | 8 | 1 | 15% | 10% | 1.5 | 5 | 7 | 5.95 | 5.355 | 5.95 | 3.855 | 19.275 | 15.5 | 3.775 | Fits
Bo | Consultant | 8 | 1 | 15% | 10% | 1 | 5 | 7 | 5.95 | 5.355 | 5.95 | 4.355 | 21.775 | 10 | 11.775 | Fits
Chandni | Analyst | 8 | 0.5 | 20% | 10% | 0.5 | 5 | 7.5 | 6 | 5.4 | 6 | 4.9 | 24.5 | 10 | 14.5 | Fits
Dinesh | Designer | 8 | 1 | 15% | 10% | 1 | 5 | 7 | 5.95 | 5.355 | 5.95 | 4.355 | 21.775 | 26 | -4.225 | Over by 4.2 h/wk
Elena | Project Manager | 8 | 1 | 20% | 5% | 3 | 5 | 7 | 5.6 | 5.32 | 5.6 | 2.32 | 11.6 | 5 | 6.6 | Fits
Firm total | [12 empty] | 98.925 | 66.5 | 32.425
Blue cells are yours to edit. Black columns are calculated, and are locked so a formula cannot be typed over.
Gross = working hours minus lunch. CWC = Gross x (1 - reserve%). Planning target = CWC x (1 - buffer%). Hard ceiling = CWC.
Committed/wk reads live from the Demand tab. Free/wk below zero means that person is overbooked.

## Demand
Job | Client | Assigned to | Man-hour estimate (h) | Target finish (weeks) | Hours/week needed | Person weekly capacity | Person committed/wk | Fit
Website rebuild | Acme | Dinesh | 40 | 4 | 10 | 21.775 | 26 | Over by 4.2 h/wk
Brand refresh | Acme | Dinesh | 30 | 3 | 10 | 21.775 | 26 | Over by 4.2 h/wk
Landing pages | Beacon | Dinesh | 18 | 3 | 6 | 21.775 | 26 | Over by 4.2 h/wk
Q3 audit | Nomad Co | Chandni | 60 | 6 | 10 | 24.5 | 10 | Fits
Data migration | Nomad Co | Bo | 50 | 5 | 10 | 21.775 | 10 | Fits
Strategy retainer | Beacon | Amir | 30 | 4 | 7.5 | 19.275 | 15.5 | Fits
Ops review | Beacon | Amir | 24 | 3 | 8 | 19.275 | 15.5 | Fits
Coordination | Internal | Elena | 20 | 4 | 5 | 11.6 | 5 | Fits
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Blue cells are yours to edit. Pick the person from the dropdown so the capacity lookup matches.
Fit compares everything assigned to that person against their real weekly capacity, so it flags the person, not the row.